## week 3
ID | Task Name | Duration (days) | Start | Finish | Dependencies | Milestone
1 | Requirement Gathering | 2 | 2025-11-01 | 2025-11-02 | 0 | ✅
2 | Data Collection | 4 | 2025-11-03 | 2025-11-06 | 1
3 | Data Cleaning/Prep | 4 | 2025-11-07 | 2025-11-10 | 2
4 | Baseline Modeling | 5 | 2025-11-11 | 2025-11-15 | 3
5 | Evaluation & Iteration | 4 | 2025-11-16 | 2025-11-19 | 4
6 | Dashboard / Demo | 3 | 2025-11-20 | 2025-11-22 | 4,5
7 | Testing | 2 | 2025-11-23 | 2025-11-24 | 6
8 | Report & Presentation | 3 | 2025-11-25 | 2025-11-27 | 7 | ✅

## Week 04 – WBS
WBS ID | Task | Deliverable | Owner | Start | Date | End | Date | Phase | Description / Notes | Estimated Cost (RM)
1.1 | Identify and collect datasets (X-ray, cough, symptoms) | List of verified data sources | Waleed Isskandar Almandari | 2025-10-10 | 2025-10-12 | Requirements & Data | Check sources for quality & license | Requirements & Data | Check sources for quality & license | 150
1.2 | Perform data cleaning, labeling and splitting | Cleaned and labeled dataset | Yaseen Mohammed Awad | 2025-10-13 | 2025-10-16 | Requirements & Data | Remove noise + balance dataset | Requirements & Data | Remove noise and balance dataset | 200
1.3 | Document data ethics & usage policy | Data ethics note (`docs/data_ethics.md`) | Alwaleed Hassan Elyas | 2025-10-17 | 2025-10-18 | Requirements & Data | Follow university data policy | Requirements & Data | Follow university data policy | 0
2.1 | Design CNN architecture and parameters | Model design document (`reports/model_plan.md`) | Yaseen Mohammed Awad | 2025-10-19 | 2025-10-21 | Model Design & Training | Plan layers and hyper-parameters | Model Design & Training | Plan model layers and hyperparameters | 80
2.2 | Train CNN and evaluate baseline accuracy | Trained model (`models/v1`) | Yaseen Mohammed Awad | 2025-10-22 | 2025-10-25 | Model Design & Training | Use Colab GPU for training | Model Design & Training | Use Colab GPU for training | 200
2.3 | Integrate trained model into Flask API | Functional backend (`src/api/app.py`) | Alwaleed Hassan Elyas | 2025-10-26 | 2025-10-28 | Model Design & Training | Test inference route / output | Model Design & Training | Test inference route and output | 175
3.1 | Develop React dashboard UI | UI prototype (`src/web/`) | Alwaleed Hassan Elyas | 2025-10-29 | 2025-10-31 | Evaluation & Dashboard | Create basic layout and graphs | Evaluation & Dashboard | Create basic layout and graphs | 100
3.2 | Connect API to dashboard for prediction | Integrated demo (`demo.mp4`) | Waleed Isskandar Almandari | 2025-11-01 | 2025-11-03 | Evaluation & Dashboard | Test full system workflow | Evaluation & Dashboard | Test full system workflow | 80
4.1 | Write final report and prepare slides | Report & slides (`docs/final_report.docx`) | Team | 2025-11-04 | 2025-11-07 | Reporting & Submission | Include results and future work | Reporting & Submission | Include results and future work | 50
4.2 | Final review and submission | Final GitHub release tag (`v1.0`) | Team | 2025-11-08 | 2025-11-09 | Reporting & Submission | Upload to ULearn and GitHub | Reporting & Submission | Upload to ULearn and GitHub | 0
RM 785