## Resource List
WBS ID | Task | Resource Type | Resource Name | Qty / Hours | Description
1.1 | Collect and clean X-ray dataset | Human | Waleed Isskandar Almandari | 6 hrs | Data collection and labeling
1.2 | Model training and tuning | Human | Yaseen Mohammed Awad | 8 hrs | Train CNN and optimize hyperparameters
1.3 | Web integration (React + Flask) | Human | Alwaleed Hassan Elyas | 7 hrs | Frontend and backend integration
1.4 | Project supervision | Human | Dr. Farhan Khan | 2 hrs | Consultation and feedback
2.1 | Model development | Software | Python (Google Colab) | - | Model training environment
2.2 | Code repository | Software | GitHub | - | Version control and team collaboration
2.3 | Web frameworks | Software | React & Flask | - | System integration
3.1 | GPU computing | Hardware | Cloud GPU Instance | 10 hrs | Model training hardware
3.2 | Workstations | Hardware | Personal laptops | 3 units | Development and testing
4.1 | Meetings & coordination | Other | MS Teams | - | Team communication
4.2 | Scheduling | Other | MS Project | - | Timeline tracking

## Task Cost Estimation
Task | Resource | Hours/Qty | Rate (RM/hr or flat) | Total Cost (RM)
Collect and clean X-ray dataset | Waleed Isskandar Almandari | 6 | 25 | 150
Model training and tuning | Yaseen Mohammed Awad | 8 | 25 | 200
Web integration (React + Flask) | Alwaleed Hassan Elyas | 7 | 25 | 175
Project supervision | Dr. Farhan Khan | 2 | 40 | 80
GPU Computing | Cloud GPU Instance | 10 | 8 | 80
Tools and Software | Colab, React, Flask |  | 50 | 50

## Budget Summary
Cost Category | Example Items | Subtotal (RM)
Human Resources | Team members + Supervisor | 605
Hardware / Cloud | GPU instance + laptops | 130
Software / Licenses | Colab, React, Flask | 50
Communication | MS Teams meetings
Total Estimated Cost |  | 785

## Cost-Schedule Link
WBS ID | Task | Start Date | End Date | Estimated Cost (RM) | Milestone Impact
1.1 | Collect and clean X-ray dataset | Week 1 | Week 2 | 150 | Data Ready
1.2 | Model training and tuning | Week 3 | Week 4 | 200 | Model Performance Validated
1.3 | Web integration | Week 5 | Week 6 | 175 | System Integration Ready
1.4 | Project supervision | Week 6 | Week 7 | 80 | Supervisor Approval
3.1 | GPU computing (cloud) | Week 3–4 | - | 80 | -
4.1 | Reporting & Presentation | Week 8 | Week 9 | 100 | Final Submission